## Sheet1
Active (Funded) Fish Passage Remediation Locations
This table represents current funding information available for the 27 Active locations that are being developed. As these locations are further developed through the design, permitting and construction process, information and costs may be updated.
No. | District | County – Route – Post Mile | EA | Project ID | Project Name | Programming Document | PAD ID # | Stream Name | Estimated Year of Construction | Estimated Year Construction Completed | Total Programmed Fish Passage Project Funding[1] | Contributions by Others | Notes
1 | 1 | Del Norte – 101 – PM 39.78 | 0F310 | 115000108 | Dr. Fine Bridge Mitigation | SHOPP | 707134 | Dominie Creek | 2019/20 | 22/23 | 10009000
2 | 1 | Del Norte – 199 – PM 2.56 | 48801 | 119000016 | Clarks Creek | SHOPP | 707139 | Clarks Creek | 2020/2021 | 22/23 | 2546000
3 | 1 | Del Norte – 199 – PM 31.31 | 48801 | 119000016 | Griffin Creek | SHOPP | 707137 | Griffin Creek | 2020/21 | 22/23 | 2546000
4 | 1 | Humboldt – 96 – PM 8.83 | 0G160 | 116000131 | Campbell Creek | SHOPP | 707141 | Campbell Creek | 2019/20 | 19/20 | 529914
5 | 1 | Humboldt – 101 – PM 124.49 | 0F960 | 1160000109 | Little Lost Man Creek | SHOPP | 713025 | Little Lost Man Creek | 2019/20 | 21/22 | 10178000
6 | 1 | Humboldt – 254 – PM 4.20 | 0E790 | 115000021 | Fish Creek | SHOPP | 707157 | Fish Creek | 2022/23 | 24/25 | 4685000
7 | 1 | Humboldt – 254 – PM 40.83 | 0H240 | 117000140 | Multiple Culverts | SHOPP | 722439 | Chadd Creek | 2025/26 | 27/28 | 6000000
8 | 2 | Shasta – 5 – PM R24.54 | 4G530 | 214000023 | Districtwide Scour Project | SHOPP | 759970 | Spring Branch Creek | 2020/21 | 22/23 | 5067000
9 | 2 | Shasta – 36 – PM 3.6 | 2H620 | 216000154 | Harrison Gulch | SHOPP | 737281 | Harrison Gulch | 2020/21 | 22/23 | 524698
10 | 2 | Siskiyou – 5 – PM 27.2 | 2H060 | 216000081 | Parks Creek | SHOPP | 720504 | Parks Creek | 2018/19 | 20/21 | 354828
11 | 2 | Siskiyou – 96 – PM 43.5 | 1H590 | 216000025 | Cade Creek | SHOPP | 720541 | Cade Creek | 2023/24 | 27/28 | 7134000 | $50,000[2]
12 | 2 | Siskiyou – 96 – PM 57.0 | 1H590 | 216000025 | Portuguese Creek | SHOPP | 707169 | Portuguese Creek | 2023/24 | 27/28 | 7134000 | 50000
13 | 4 | Alameda – 84 – PM 121.1 | 16030 | 400000429 | Niles Canyon Improvement Project | SHOPP | 713729 | Stonybrook Creek | 2020/21 | 23/24 | 4500000
14 | 4 | Napa – 121 – PM 0.75 | 4G210 | 412000310 | Huichica Creek Bridge | SHOPP | 714975 | Huichica Creek | 2020/21 | 24/25 | 20469000
15 | 4 | San Mateo – 280 – PM 0.01 | 4J850 | 416000028 | Seismic Restoration | SHOPP | 705760 | Los Trancos Creek | 2021/22 | 22/23 | 10432000
16 | 4 | Santa Clara – 85 – PM 12.6 | 2J780 | 415000017 | Structure Rehab | SHOPP | 733945 | San Tomas Aquinas Creek | 2020/21 | 21/22 | 5739000
17 | 4 | Sonoma – 1 – PM 15.1 | 0A020 | 400000129 | Gleason Beach Highway Realignment | SHOPP | 733223 | Scotty Creek | 2020/21 | 23/24 | 22500000
18 | 5 | Santa Barbara – 1 – PM 15.61 | 0A050 | 500000007 | Salsipuedes Creek Bridge Replacement | SHOPP | 700085 | Salsipuedes Creek | 2018/19 | 21/22 | 14098000
19 | 5 | Santa Barbara – 101 – PM 5.6 | 0N700 | 518000113 | South Coast HOV | STIP | 734310 | Arroyo Parida Creek | 2020/21 | 25/26 | 6500000
20 | 5 | Santa Barbara – 101 – PM 9.4 | 0N700 | 500000131 | South Coast HOV | STIP | 705161 | Romero Creek | 2020/21 | 25/26 | 4500000 |  | 2022 start; maybe 2023
21 | 5 | Santa Barbara – 101 – PM | 0N700 | 500000131 | South Coast HOV | STIP | 734342 | San Ysidro Creek | 2020/21 | 25/26 | 4500000 |  | 2022 start; maybe 2023
22 | 5 | Santa Barbara – 154 – PM 21.3 | 1H630 | 516000113 | Culvert Repair | SHOPP | 735549 | Bear Creek | 2020/21 | 22/23 | 2942950
23 | 5 | Santa Barbara – 192 – PM 15.5 | 39610 | 500000514 | Emergency Bridge Replacement | SHOPP | 706239 | Arroyo Parida Creek | 2020/21 | 23/24 | 8129954
24 | 7 | Los Angeles – 1 – PM 50.3 | 31350 | 715000090 | Solstice Creek Bridge | SHOPP | 705781 | Solstice Creek | 2021/22 | 25/26 | 36248131 |  | In design currently, PS&E; applying for permits soon.
25 | 7 | Ventura – 33 – PM 7.62 | 29130 | 712000083 | San Antonio Creek Bridge | SHOPP | 713867 | San Antonio Creek | 2019/20 | 22/23 | 10798892 |  | Consists of main project and "follow-up" project with fish passage component; in process of getting final fish passage design (Mike Love) approved;
26 | 11 | San Diego – 76 – PM 29.5 | 42220 | 1115000179 | Culvert Replacement | SHOPP | 712680 | Pauma Creek | 2026/27 | 29/30 | 21963490
27 | 12 | Orange – 5 – PM 11.30 | PEER | PEER | I-5/Trabuco | Local Agency | 706807 | Trabuco Creek | N/A | N/A | - | $1,100,000[1] | CDFW just funded the next iteration of the design to take it to 100% and support permitting and CEQA;
Total Estimated Fish Passage Funding Investment | [10 empty] | 230029857 | 1200000
[1] This column lists the programmed transportation funding for fish passage remediation locations. The bold and underlined costs are estimates of average costs for the identified fish passage solution type, since the true programmed costs include larger project efforts which are not related to fish passage.
[1] The US Fish and Wildlife Service provided a $100k grant for Cade and Portuguese Creek locations. The grant is from a US Department of the Interior program, ‘15.680 Fish and Wildlife Assistance’.
[1] Project managed by CalTrout with contributions; $173,873 – California Department of Fish and Wildlife, $383,890 – National Fish and Wildlife Foundation, and $534,000 – California Wildlife Conservation Board.